## Group member 1
To-do list
To be completed by: |  |  |  | Name: Philip Charles
Deadline: |  |  |  | Date: 12/8/23
Project 2 Midterm
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting - Planning | 2023-11-19 | 2023-11-19 |  | 0
100% | CDM,LDM and PDM Design | 2023-11-20 | 2023-12-03 |  | 13
100% | Group Meeting | 2023-12-04 | 2023-12-04 |  | 0
100% | DDL and PostgreSQL Migration | 2023-12-05 | 2023-12-07 |  | 2
100% | Documentation | 2023-12-07 | 2023-12-07 |  | 0

## Group member 2
To-do list
To be completed by: |  |  |  | Name: Sammi Wong
Deadline: |  |  |  | Date: 12/8/23
Project 2 Midterm
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2023-11-19 | 2023-11-19 |  | 0
100% | Research Trigger functionalities | 2023-11-20 | 2023-12-03 |  | 13
100% | Group Meeting | 2023-12-04 | 2023-12-04 |  | 0
100% | Apply triggers to project | 2023-12-05 | 2023-12-08 |  | 3

## Group member 3
To-do list
To be completed by: |  |  |  | Name: Caleb Busch
Deadline: |  |  |  | Date: 12/8/23
Project 2 Midterm
% done | Phase | Start By | Original Due By | Numer Of Days | Revised Due By | Revision Notes
100% | Group Meeting | 2023-11-19 | 2023-11-19 | 0
100% | Research MongoDB functionalities | 2023-11-20 | 2023-12-03 | 13
100% | Group Meeting | 2023-12-04 | 2023-12-04 | 0
100% | Apply MongoDB Migration | 2023-12-05 | 2023-12-08 | 3

## Group member 4
To-do list
To be completed by: |  |  |  | Name: Robert Antenorcruz
Deadline: |  |  |  | Date: 12/8/23
Project 2 Midterm
% done | Phase | Start By | Original Due Date | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2023-11-19 | 2023-11-19 |  | 0
100% | Review Domains, Validations and PDM related subjects throughout semester | 2023-11-20 | 2023-12-03 |  | 13
100% | Group Meeting | 2023-12-04 | 2023-12-04 |  | 0
100% | Overlook PDM group model for Submission | 2023-12-05 | 2023-12-08 |  | 3

## Group member 5
To-do list
To be completed by: |  |  |  | Name: Chetanya Sharma
Deadline: |  |  |  | Date: 12/8/23
Project 2 Midterm
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2023-11-19 | 2023-11-19 |  | 0
100% | Review CDM and LDM related subjects throughout semester | 2023-11-20 | 2023-12-03 |  | 13
100% | Group Meeting | 2023-12-04 | 2023-12-04 |  | 0
100% | OverLook CDM and PDM group model | 2023-12-05 | 2023-12-08 |  | 3

## Group member 6
To-do list
To be completed by: |  |  |  | Name: Djiedjom Ange Lionel Gbonkou
Deadline: |  |  |  | Date: 12/8/23
Project 2 Midterm
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2023-11-19 | 2023-11-19 |  | 0
100% | Review MySQL Syntax and Migration Process | 2023-11-20 | 2023-12-03 |  | 13
100% | Group Meeing | 2023-12-04 | 2023-12-04 |  | 0
100% | Apply MySQL Migration to Project | 2023-12-05 | 2023-12-08 |  | 3